## Sheet1
Author - Eric Hanks |  | Functionality Testing Record
Date | Test Case/Scenario | Relevant Scripts | Responsible Personnel | Expected Test Results | Actual Test Results | Suggested Actions | Team Endorsement
2020-03-22 | Bullet Collisions | Bullet, Player, enemey | Eric | The bullet gameobject is destroyed when it comes in contact with any collider, and an enemy will take damage if a bullet enters their collider | Bullets were not be destroyed and were pushing the enemys and player around. | The oncollisionenter function needs be corrected, with an if statement that checks the tag of the collider it enters for an "Enemy" tag and take the damage value of the bullet
2020-03-25 | Saving Highscore | Player, Logreader, Textfile manager, Timertrigger | Eric | The highscore of both the time survided and the points collected should be saved and reloading upon another run | High score did not save, UI elements for both time and score displayed no changes | Rectify UI scripting and updating and make sure the UI is set to what it needs to be, check that the score is being stored properly upon the Die function executing.
2020-03-26 | Instantiating Enemies | Enemy, Spawnplat, timertrigger, player | Eric | Enemies instantiate ontop of the spawn platforms at a normal size and start chasing the player | Enemies instantiated, but at the same width as the spawn platform and chased the player | Rewrite the instantiate method on the spawn platform to use the enemy objects rotation but the spawn platforms position